Table of Contents
1.
INTRODUCTION
2.
SCOPE
3.
QUALITY OBJECTIVES
3.1 Primary Objectives
3.2 Secondary Objectives
4.
TEST APPROACH
4.1 Test Automation
5.
ROLES AND RESPONSIBILITIES
6.
ENTRY AND EXIT CRITERIA
6.1 Entry Criteria
6.2 Exit Criteria
7.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
7.1 Suspension criteria
7.2 Resumption criteria
8.
TEST STRATEGY
8.1 QA role in test process
8.2 Bug life cycle
8.3 Testing types
8.4 Bug Severity and Priority Definition
9.
RESOURCE AND ENVIRONMENT NEEDS
9.1 Testing Tools
9.2 Configuration Management
9.3 Test Environment x Support level
10.TEST SCHEDULE
11.APPROVALS
12.TERMS/ACRONYMS

---
Test Plan
Project “Drom”
1.
INTRODUCTION
Customer wants a perfect website, which passes the full cycle of manual and
automation testing.
The Test
Plan has been created to facilitate communication within the team
members.
This document describes approaches and methodologies that will apply to
the functional
testing of
the https://www.drom.ru/.
It
includes the objectives,
test
responsibilities,
entry and exit
criteria,
scope,
schedule major milestones,
entry and
exit
criteria
and approach.
This
document
has
clearly identified what
the test
deliverables will be.
2.
SCOPE
The document
mainly targets
the GUI
testing and validating data in report
output as per Requirements Specifications provided by Client.
2.1 Functions to be tested:
●
GUI
●
Search Logic
●
Announcement placement functionality
●
Performance
●
Security
3.
QUALITY OBJECTIVES
3.1 Primary Objectives
A primary objective of
testing is
to:
assure that
the system meets the full
requirements,
including
quality
requirements
(functional
and
non-functional
requirements) and fit
metrics for each quality requirement and satisfies the use case
scenarios
and
maintain
the
quality
of
the
product.
At
the
end of
the
project

---
development
cycle,
the user should find that
the project
has met or exceeded all of
their expectations as detailed in the requirements.
Any changes,
additions,
or deletions to the requirements document, Functional
Specification,
or Design Specification will
be documented and tested at
the highest
level of quality allowed within the remaining time of the project and within the ability
of the test team.
3.2 Secondary Objectives
The secondary objectives of testing will be to: identify and expose all issues and
associated risks, communicate all known issues to the project team, and ensure that all
issues are addressed in an appropriate matter
before release.
As an objective,
this
requires careful and methodical testing of the application to first ensure all areas of the
system are scrutinized and,
consequently,
all
issues
(bugs)
found are dealt
with
appropriately.
4.
TEST APPROACH
The
approach
that
is
used
is
Analytical
therefore,
in
accordance
with
requirements-based strategy, where an analysis of the requirements specification forms
the basis for planning,estimating and designing tests. Test cases will be created during
exploratory testing. All test types are determined in Test Strategy.
Team also must use experience-based testing and error guessing to utilize
tester’s skills and intuition, along with their experience with similar applications or
technologies.
The project is using an agile approach, with weekly iterations. At the end of
each week the requirements identified for that iteration will be delivered to the team
and will be tested.

---
5.
ROLES AND RESPONSIBILITIES
Role
Staff Member
Responsibilities
1. Acts as a primary contact for development and QA
Project
team.
Sergey Efremov
Manager
2. Responsible for Project schedule and the overall
success of the project.
1. Participation in the project plan creation/update
Sergey Efremov
QA Lead
process.
2. Planning and organization of test process for the
release.
3. Coordinating with QA analysts/engineers on any
issues/problems encountered during testing.
4. Report progress on work assignments to the PM.
QA
Oleg Shcherbakov
1. Understand requirements.
2. Writing and executing Test cases.
3. Preparing RTM.
4. Reviewing Test cases, RTM.
5. Defect reporting and tracking.
6. Retesting and regression testing.
7. Bug Review meeting.
8. Preparation of Test Data.
9. Coordinating with QA Lead for any issues or problems
encountered during test preparation/execution/defect
handling.

---
6.
ENTRY AND EXIT CRITERIA
6.1 Entry Criteria
●
All
test
hardware
platforms
must
have
been successfully installed,
configured, and functioning properly.
●
All
the necessary documentation,
design,
and requirements information
should be available that will allow testers to operate the system and judge
the correct behavior.
●
All the standard software tools including the testing tools must have been
successfully installed and functioning properly.
●
Proper test data is available.
●
The
test
environment
such as,
lab,
hardware,
software,
and system
administration support should be ready.
●
QA resources have completely understood the requirements.
●
QA resources have sound knowledge of functionality.
●
Reviewed test scenarios, test cases and RTM.
6.2 Exit Criteria
●
A certain level of requirements coverage has been achieved.
●
No high priority or severe bugs are left outstanding.
●
All high-risk areas have been fully tested, with only minor residual risks
left outstanding.
●
Cost – when the budget has been spent.
●
The schedule has been achieved.
7.
SUSPENSION CRITERIA AND RESUMPTION REQUIREMENTS
7.1 Suspension criteria
●
The build contains many serious defects which seriously or limit testing
progress.
●
Significant change in requirements suggested by client.
●
Software/Hardware problems.
●
Assigned resources are not available when needed by a test team.

---
7.2 Resumption criteria
Resumption will
only occur
when the problem(s) that
caused the suspension
have been resolved.
8.
TEST STRATEGY
8.1 QA role in test process:
●
Understanding Requirements.
●
Requirement specifications will be sent by client.
●
Understanding of requirements will be done by QA.
-
Preparing Test Cases. Test strategy includes 5 sub-tasks:
1. Manual
testing.
QA will
be preparing test
cases based on the exploratory
testing. There will be 5 test cases.
2. Automation testing. QA will transfer manual cases into automation cases with
Selenium Webdriver on Python.
3. API testing.
QA will
be preparing test
cases.
There will be 6 test cases by
method CRUD.
1 of them will
be positive,
5 - negative.
Test cases will be
automated with Postman API.
4. Website Performance Automation testing will be carried out with Lighthouse
and GTMetrix tools
5. Website
Automation
Security
test
will
be
carried
out
with
Mozilla
Observatory tool.
-
Preparing Test Matrix:
QA will
be
preparing a
test
matrix which maps
test
cases
to respective
requirements. This will ensure the coverage for requirements.
-
Reviewing test cases and matrix:
●
Peer review will be conducted for test cases and test matrix by QA Lead.
●
Any comments or
suggestions on test
cases and test
coverage will
be
provided by the reviewer respective Author of Test Case and Test Matrix.
●
Suggestions or improvements will be re-worked by the author and will be
sent for approval.
●
Re-worked improvements will be reviewed and approved by the reviewer.

---
-
Creating Test Data:
Test
data will
be created by respective QA on client's developments/test
site
based on scenarios and Test cases.
-
Executing Test Cases:
●
Test cases will be executed by respective QA on a client's
development/test site based on designed scenarios, test cases and Test
data.
●
Test result (Actual Result, Pass/Fail) will be updated in test case
document Defect Logging and Reporting: QA will be logging the
defect/bugs in Word document and JIRA, found during execution of test
cases. After this, QA will inform a respective developer about the
defect/bugs.
-
Retesting and Regression Testing:
Retesting for fixed bugs will be done by respective QA once it is resolved by the
respective developer
and bug/defect
status will
be updated accordingly.
In certain
cases, regression testing will be done if required.
-
Deployment/Delivery:
●
Once all
bugs/defects reported after
complete testing are fixed and no
other bugs are found, the report will be deployed to the client's test site.
●
Once a round of testing will
be done by QA on the client's test
site if
required Report
will
be delivered along with sample output by email to
the respective lead and Report group.
●
QA will
be submitting the filled hard copy of the delivery slip to the
respective developer.
●
Once the lead gets the hard copy of the delivery slip filled by QA and
developer, he will send the report delivery email to the client.
8.2 Bug life cycle:
All the issues found while testing will be logged into JIRA.

---
8.3 Testing types
GUI Testing:
GUI testing will include testing the UI part of the report. It covers users Report format,
look and feel, error messages, spelling mistakes, GUI guideline violations.
Exploratory testing :
Exploratory testing will include a type of software testing where Test cases are not
created in advance but QA check system on the fly. QA may note down ideas about
what to test before test execution.
Positive testing:
Positive testing will include the type of testing that can be performed on the system by
providing the valid data as input. It checks whether an application behaves as expected
with positive inputs.
Negative testing:
Negative testing will include a method of testing an application or system that ensures
that the plot of the application is according to the requirements and can handle the
unwanted input and user behavior. Invalid data is inserted to compare the output
against the given input. Negative testing is also known as failure testing or error path
testing. When performing negative testing exceptions are expected.

---
Functional Testing:
Functional testing is carried out in order to find out unexpected behavior of the report.
The characteristics of functional testing are to provide correctness, reliability,
testability and accuracy of the report output/data.
Performance Testing:
●
Check the optimal time the page is loaded
●
Check the operation of the system under load
8.4 Bug Severity and Priority Definition
Bug Severity and Priority fields are both very important for categorizing bugs
and prioritizing if
and when the bugs will
be fixed.
The bug Severity and Priority
levels will be defined as outlined in the following tables below. Testing will assign a
severity level
to all
bugs.
The Test
Lead will
be responsible to see that
a correct
severity level is assigned to each bug.
The QA Lead,
Development Lead and Project Manager will participate in bug
review meetings to assign the priority of all currently active bugs. This meeting will
be known as “Bug Triage Meetings”. The QA Lead is responsible for setting up these
meetings
on a routine basis
to address
the current
set
of
new and existing but
unresolved bugs.
Severity List
Severity
Severity
ID
Severity Description
The module/product crashes or the bug causes non-
recoverable conditions. System crashes, GP Faults, or
1
Highest
database or file corruption, or potential data loss, program
hangs requiring reboot are all examples of a Severity 1 bug.
2
High
Major system component unusable due to failure or incorrect

---
functionality.
Severity 2 bugs cause serious problems such as a
lack of functionality, or insufficient or unclear error messages
that can have a major impact to the user, prevents other areas
of the app from being tested, etc. Severity 2 bugs can have a
work around, but the work around is inconvenient or difficult.
Incorrect functionality of component or process. There is a
3
Medium
simple work around for the bug if it is Severity 3.
4
Low
Documentation errors or signed off Severity 3 bugs.
Priority List
Priority Priority Level
Priority Description
This bug must be fixed immediately; the product cannot
1 Highest
ship with this bug.
These are important problems that should be fixed as soon
2 High
as possible. It would be an embarrassment to the company
if this bug shipped.
The problem should be fixed within the time available. If
3 Medium
the bug does not delay the shipping date, then fix it.
It is not important (at this time) that these bugs be
addressed. Fix these bugs after all other bugs have been
4 Low
fixed. Enhancements/ Good to have features incorporated-
just are out of the current scope.
5
Lowest
Documentation errors or signed off Low 4 bugs.

---
9.
RESOURCE AND ENVIRONMENT NEEDS
9.1 Testing Tools
Process
Tool
Test case creation
Microsoft Word, Microsoft Excel, JIRA
Test case tracking
JIRA,
Confluence
Frontend Manual, Frontend Selenium
Test case execution
Automation with Python, API automation
with Postman
Test case management
Microsoft Excel, JIRA, Confluence
Defect management
Microsoft Word, JIRA, Confluence
Test reporting
JIRA
Check list creating
Microsoft Excel, JIRA
9.2 Configuration Management
●
Documents CM: SVN
●
Code CM: Git
9.3 Test Environment x Support level 1 (browsers):
●
Windows 10 : Chrome (Version 107.0.5304.88) ),
Firefox (Version 107.0.1 )

---
10.TEST SCHEDULE
Task Name
Time for task
Effort
Comments
Test Planning
16 hours/2
documentation
days
Review Requirements
8 hours/1 day
documents
Create test basis
8 hours/1 day
with team
flex
FRONT-END
Exploratory testing
4 hours/0,5 day
Positive testing
4 hours/0,5 day
Automating of the
16 hours/2
days
manual test-cases
API TESTING
Exploratory testing
4 hours/0,5 day
Positive testing
4 hours/0,5 day
Negative testing
4 hours/0,5 day
Automating of the
16 hours/2
days
manual test-cases
Performance testing
4 hours/0,5 day
Security testing
4 hours/0,5 day
11.APPROVALS:
Project Manager
QA Lead
Name
Sergey Efremov
Sergey Efremov

---
Signature
12.TERMS/ACRONYMS
The below terms are used as examples, please add/remove any terms relevant to
the document.
TERM/ACRONYM
DEFINITION
API
Application Program Interface
GUI
Graphical user interface
PM
Project manager
UAT
User acceptance testing
CM
Configuration Management
QA
Quality Assurance
Requirements Traceability
RTM
Matrix